## Sheet1
		Week
Task	Description	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38
		21/10/2024	28/10/2024	04/11/2024	11/11/2024	18/11/2024	25/11/2024	02/12/2024	09/12/2024	16/12/2024	23/12/2024	30/12/2024	06/01/2025	13/01/2025	20/01/2025	27/01/2025	03/02/2025	10/02/2025	17/02/2025	24/02/2025	03/03/2025	10/03/2025	17/03/2025	24/03/2025	31/03/2025	07/04/2025	14/04/2025	21/04/2025	28/04/2025	05/05/2025	12/05/2025	19/05/2025	26/05/2025	02/06/2025	09/06/2025	16/06/2025
Literature Review
Framing the project	Reading Literatures to get a better understanding of the problem, focusing on urban inequalities
Methodology Research	Understanding existing methodologies to frame the project's (ML + combinatorial)
Validation Methods Research	Research on how existing literature measure/validate
Project Development
Data Collection	Find + Collect census data
Data Cleaning	Cleaning census data
Matching census data with GEOJSON data on LSOA borders	Make sure that the areas on a map contains census data for spatial partitioning later
Methodology Formulation	Formulating MDP with Voronoi tessellation (On paper)
Spatial Partitioning attempt 1	Working on coding Voronoi tessellation + visuals
MDP Development	Coded the structure of the MDP
MDP + Voronoi	Ran sanity tests to see performance
More Methodology research	Voronoi did not perform well, research for more methods to experiment
Spatial Partitioning attempt 2	Working on coding H3 index based spatial partitioning
MDP + H3	Ran sanity tests
Validation Method Development	Coded + Debug the static validation methods
SUMO Research	Supervisor recommend looking at a more dynamic way to simulate impact
Map collection + cleaning	Preparing the map used in SUMO (Ensure valid edges, correct infrastructure exported, etc.)
SUMO Implementation	Development + Debug + work around to make SUMO simulation work
Report Writing
Report Writing	Writing the report + proof reading
Presentation Prep	Preparing the presentation for Viva